## Master List Templates
Id | Type | Name | Values | Prompting Name
c516fb33-e8c2-44ac-a644-017396b54187/14 | checklist | EWi1e1 - 1 Internal Layer - 1 External Layer - Batts |  | EW_000x
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Step 1 - Framing and Inside Layers
d187e829-2758-4e91-97f8-a88dbbb0b23c | checkpoint-no-value | Step 1 - Framing and Inside Layers
6c40d86f-4a6e-5387-999b-7f1080b688c0 | button | Framing check for square. | Yes,No
a0e9763e-ffa1-5170-9bde-cba689cc0226 | button | Structural fixings in frame are as per drawings. | Yes,No
a7182194-fc17-5384-b21f-7f138a568d97 | button | Slings installed as per drawings. | Yes,No,Not Applicable
78822da9-76b9-5de9-bbf1-1411ae565a70 | note | Take Photos of frame, fixings and connections.
deca3466-fe55-584e-bce0-045bf10bceb9 | section | Step 2 - Inside Lining
818f14d4-7bbb-462c-a51d-3d5df70677a0 | checkpoint-no-value | Step 2 - Inside Lining
0a506d51-0ecc-5bce-96bb-435b695c2e22 | button | Internal layer 1 - product. | OSB15,OSB22,Ply UT 15,Ply H3 15,GIB10,GIB 13,GIB 16,Other,N/A
7899949a-9ad3-5468-9999-3882852fd64e | button | Internal layer 1 - fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
bc3d7ab3-c1c9-5a95-9759-8cf1ee26277e | button | Internal layer 1 - fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
4dcb7204-47f0-5111-90c5-52940cce07fa | section | Step 3 - Services
93998e54-e5f5-4a84-8681-e3ab37ba9108 | checkpoint-no-value | Step 3 - Services
7b2ebf8e-57c7-5606-9a9a-08f2129a5556 | button | Services - Fire rated wall, use fire rated flush box. Do not alter flush boxes. | Yes,No,Not Applicable
5babd0ba-63f3-526b-bc8b-907f5880fd42 | button | Services - Conduits terminated and run to best practice and as per drawings. | Yes,No,Not Applicable
54f66945-da69-52ff-a441-95d6b8b8c5a8 | button | Services - Airtightness - penetrations are sealed. | Yes,No,Not Applicable
efa6ece0-71e3-5fc7-a495-dbf82ff6ec42 | button | Services - Fire rated wall, all penetrations treated as per drawings (i.e. gib lined or so) | Yes,No,Not Applicable
773b35be-26d2-58dd-ae32-bd1ea868cde2 | note | Take photos of flush boxes, fire treated penetrations, conduit terminations.
987d8171-da86-5327-8ecd-f635ef8df782 | section | Step 4 - Insulation
2bde2228-bcc1-4098-89ff-ff5679f4c5ca | checkpoint-no-value | Step 4 - Insulation
e1e40c7c-e13e-50af-8599-0dfc08ad30c3 | button | Insulation as per drawing. Tight fit, no gaps, no squeeze. | R2.6,R2.8,R4.1,None
a5a5ba6d-f06a-5055-9d36-e7554ac44017 | note | Take photos of finished insulation.
5fd14ab0-6fc4-52c1-9326-7079ea2fb858 | section | Step 5 - External Layer
f038da47-415d-4d5c-88a8-d76860b98808 | checkpoint-no-value | Step 5 - External Layer
fe64a9c8-e7ba-5e95-ac00-5c40eda16e8c | button | External layer 1 - product. | Membrane,Ply H3 15,Ply H3 17,Ply H3 19,WEATHERLINE10,WEATHRLINE13,GIB13,GIB16,Other,N/A
976fc9cb-112c-5cd7-a288-3dbc66d4199e | button | External layer 1 - fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
7c4a0ee1-0275-55a3-a983-7418a4eac84b | button | External layer 1 - fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
7ac90f41-3e70-52c1-8588-940aea2525ea | note | External layer 1 - take photos of fixings.
186de131-c455-55c4-a360-7b618e9bd410 | section | Step 6 - Layer 2
25d6ba27-881e-4acd-85d3-c9b989f3dea1 | checkpoint-no-value | Step 6 - Layer 2
7fe74c10-08aa-588c-9286-36e2828d9927 | button | External layer 1 - taping of joints, openings as per manufacturer specification. | GIB Weatherline Tape,Proclima tape,Sika tape,Rothoblaas tape,Marshall tape,Other
c426f591-5487-5a99-9373-5b58667bc595 | button | Panel completed, no defects, no damage. | Yes,No
038f98a0-5011-5744-9b64-04c30c545eb1 | note | External layer 1 - take photos of tapes and final panel.
b278e6db-2ae6-55fd-8445-77adeeddd920 | section | Step 7 - Final Sign Off
914f8688-b0f0-51ca-8fef-fe47eb9485b6 | checkpoint | Step 6 - Final Sign Off
ad92bca8-f00b-5c1d-af7e-a8a71e5fc1ca | signoff | Sign off from Shift Leader.