## Master List Templates
Id | Type | Name | Values | Prompting Name
acc209ed-3164-4e66-bf98-bc6580153ff0/13 | checklist | Ri1e3BI - Roof Panel - 1 Internal Layer - 3 External Layer - Blow In |  | R_000x
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Step 1 - Framing and Inside Layers
299fc639-f683-4971-af35-b4f4436fe163 | checkpoint-no-value | Step 1 - Framing and Inside Layers
cb70f9ba-059d-5891-8e93-cff46453fc58 | button | Framing check for square. | Yes,No
f13d144d-8ca2-50ee-a227-e9dde6432978 | button | Structural fixings in frame are as per drawings. | Yes,No
5680fb88-fe3c-54c0-b29f-c0fae6bf5638 | button | Slings installed as per drawings. | Yes,No,Not Applicable
ecc21a8a-2836-5932-990b-9159337d4d44 | note | Take Photos of frame, fixings and connections.
284b46b0-2d5f-5309-bb26-fb56ded652a1 | section | Step 2 - Passive Fire Lining
a10840c0-8df7-49d4-b56c-f921b10b8000 | checkpoint-no-value | Step 3 - Passive Fire Lining
e6488f8e-cef1-413d-aff0-31ea49bb9ed1 | button | Product | GIB10 Fyreline,GIB13 Fyreline,GIB16 Fyreline,Not Applicable
e637267f-8634-4ad3-b9eb-a6ba6b624151 | note | With black marker write on Fyreline the thicknes of the GIB used. Take good photos of the Fyreline, from several sides. If necessary.
ef920534-d80f-5381-9d98-c3d91f1c45e9 | section | Step 3 - Internal Layer 1
61a22b20-8b6e-460b-842c-daa831427dd8 | checkpoint-no-value | Step 2 - Internal Layer 1
3930f7d5-a074-596a-929d-cadc80cc520c | button | Internal layer 1 - product. | OSB15,OSB22,Ply UT 15,Ply H3 15,GIB10,GIB13,GIB16,OTHER,NOT APPLICABLE
0066ce97-7ced-5091-8ca7-3f305286d3c2 | button | Internal layer 1 - fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
17fbd79e-42ab-582a-88ad-e5fe33829659 | button | Internal layer 1 - fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
5cc30ccd-7dfb-578d-8482-19f9712b4e63 | section | Step 4 - Services
4c152253-53eb-4d18-8d43-c8e33387ceda | checkpoint-no-value | Step 4 - Services
b458853d-0479-5b91-be71-8c59c330460e | button | Services - Conduits terminated and run to best practice and as per drawings. | Yes,No,Not Applicable
69642b7c-2dcf-581c-8b1c-4e95f019e633 | button | Services - Airtightness - penetrations are correctly sealed. | Yes,No,Not Applicable
5d9eb2d4-0620-5b6e-af46-ee297e8c9f4d | note | Take photos of flush boxes, fire treated penetrations, conduit terminations.
557136d7-fb6c-5553-bd5b-edad5be15998 | section | Step 5 - External Layer 1 (Sheet Material)
4dea3272-6b14-4583-a32a-5091d844528f | checkpoint-no-value | Step 5 - External Layer 1 (Sheet Material)
79d8c981-cb48-58a8-a80a-ad0969920584 | button | External layer 1 - Product. | DHF,Ply H3 15,Ply H3 17,Ply H3 19,Other,Not applicable
d6195685-0f3f-530b-ae7a-73e0e32728fa | button | External layer 1 - Fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
c085431f-2f30-5779-9533-d684b315e234 | button | External layer 1 - Fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
15e7e520-ef5e-4d04-9da5-0287593b339b | button | Access or Removable sheets are labeled with ACCESS PANEL sticker | Yes,No,Not Applicable
076b5688-003a-56ce-8902-b63c264eaa28 | note | External layer 1 - Take photos of panel, sheets and fixings.
60c716b6-6d31-5139-afb6-9336f599ce44 | section | Step 6 - External Layer 2 (Membrane)
0f763769-f6e0-4ddc-aec5-e69470eb36b4 | checkpoint-no-value | Step 6 - External Layer 2 (Membrane)
f1995e07-a37d-4cbf-8c13-be9ba5e92582 | button | Product | Proclima Mento 3000 / Connect,Proclima Adhero,Other
bd3f4aa4-dbed-435b-b7a9-4d028a92681e | button | Fixings | None,Galvanised Staples
70fc726b-9cc4-4422-beba-e69da9c25dd0 | button | Membrane joints and laps as per specifications or shop drawings | Yes,No
6965d286-8ccd-4169-8fcb-76cdec3525fe | button | Membrane overhangs as per shop drawings | Yes,No
1d66523a-3568-471a-925e-1326d711f545 | note | Take photos of panel with membrane and membrane joint (fold up if possible)
e8687eb5-969c-541c-90f2-ef4cb37516c0 | section | Step 7 - External Layer 3 - Counter battens
1f9a265b-f1e0-4367-bc9e-0099f0815afc | checkpoint-no-value | Step 7 - External Layer 3 - Counter battens
e4388cc3-6bb2-4b8e-9aa6-3c3543aa4242 | button | Counter batten size | 45x20 (actual dimension),75x45 (actual dimension)
dcbfccc0-7a57-44c8-bfe9-2afd3d827d04 | button | Product for tape under counter battens | Proclima Naideck,Not Applicable
f5755ea9-d092-4db3-84be-2008e169fe7a | note | Take Photo of panel with counter battens. Add close up of tape under battens.
4a0828d1-5006-5726-8170-d4f2778c1623 | section | Step 8 - Blow In Insulation
e152c33d-ea58-40bf-94db-33f22dfd26d7 | checkpoint-no-value | Step 8 - Blow In Insulation
8485d869-7aac-50f9-861e-926f368309c4 | button | Blow-In results meet design criteria and quality check sheet. | Yes,No
d91c2fcc-374c-5d54-8666-2e445fcf7cad | note | Take photo of filled out Blow-In quality check sheet and installation holes prior to taping them close.
01c8fd12-8401-5a2b-9ac9-669d4763e3d7 | section | Step 9 - Final Sign Off
c48dffd6-63de-429c-998f-ed7ebdad3374 | checkpoint | Step 9 - Final Sign Off
da9d4921-8465-4b0f-9db2-50513868c4fe | signoff | Sign off from Shift Leader.