## Master List Templates
Id | Type | Name | Values | Prompting Name
8f9b8b3d-e489-4162-9b71-c9f68eac4001/2 | checklist | Ri1e3Batt - Roof Panel - 1 Internal Layer - 3 External Layer - Insulation Batts |  | R_000x
3774480b-2202-5512-814c-5cd8ca745766 | section | Step 1 - Framing and Inside Layers
b6c81218-0325-5adc-9670-f13ec307b57d | checkpoint-no-value | Step 1 - Framing and Inside Layers
ffb006d6-53aa-5678-8e78-d9b8f4e70679 | button | Framing check for square. | Yes,No
e7955041-42de-5aa2-9a1b-f81d3a1d0c58 | button | Structural fixings in frame are as per drawings. | Yes,No
d0cce61f-4b18-505e-b63a-bf80d0376a79 | button | Slings installed as per drawings. | Yes,No,Not Applicable
9e9a6f9f-acc6-586b-a3f9-bb138557c8fb | note | Take Photos of frame, fixings and connections.
8ba6de28-724a-5365-8d8b-879f29bfb3a1 | section | Step 2 - Passive Fire Lining
ebedea36-4d5e-53d1-b2ad-8b37b5ad4fed | checkpoint-no-value | Step 3 - Passive Fire Lining
c252705b-8925-52ad-b92e-27811efa2e75 | button | Product | GIB10 Fyreline,GIB13 Fyreline,GIB16 Fyreline,Not Applicable
d6b53946-3a5f-5499-b14c-bdb1f6709fde | note | With black marker write on Fyreline the thicknes of the GIB used. Take good photos of the Fyreline, from several sides. If necessary.
e4947605-bc8c-5ddd-a99e-9f7544a7366c | section | Step 3 - Internal Layer 1
7a425182-e4e6-50f7-ba25-5b5e6bfd6d52 | checkpoint-no-value | Step 2 - Internal Layer 1
43bda50e-0932-5e0e-b3ea-fdff7e94d469 | button | Internal layer 1 - product. | OSB15,OSB22,Ply UT 15,Ply H3 15,GIB10,GIB13,GIB16,OTHER,NOT APPLICABLE
e9661429-1fb2-5079-a7cb-cbf5108156c0 | button | Internal layer 1 - fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
3f50a7ad-3aae-5f62-ae68-f058e6053947 | button | Internal layer 1 - fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
5cc30ccd-7dfb-578d-8482-19f9712b4e63 | section | Step 4 - Services
1e1d467b-7661-5519-b98e-9c939d6809a7 | checkpoint-no-value | Step 4 - Services
07f94c0c-8493-552b-8e6b-fb9e6df8739f | button | Services - Conduits terminated and run to best practice and as per drawings. | Yes,No,Not Applicable
3bf4bb13-964c-5b69-8e83-7bb3a8cd0a19 | button | Services - Airtightness - penetrations are correctly sealed. | Yes,No,Not Applicable
56607a93-dbd9-5466-9826-f158d6e0c9a4 | note | Take photos of flush boxes, fire treated penetrations, conduit terminations.
88cdd18a-5700-573c-b098-d870d226a951 | section | Step 5 - Blow In Insulation
798217ec-4419-553b-88e0-f38dc578351a | checkpoint-no-value | Step 5 - Insulation
af164f88-6741-530f-8f9c-230795b7a6be | button | Insulation as per drawing. Tight fit, no gaps, no squeeze. | Ceiling R4.1,Ceiling R5.2,Ceiling R7.0,Ceiling R8.0,Skillion R5.0,Skillion R6.0,Skillion R7.4,Blow-in later,None
e4f8c515-8a97-5998-8371-8a1a6ce82114 | note | Take photos of finished insulation.
fce960cf-fa10-55bf-bd15-526ae0b7cef7 | section | Step 6 - External Layer 1 (Sheet Material)
0782f1c3-d75f-5a61-a611-17bd74b92f59 | checkpoint-no-value | Step 6 - External Layer 1 (Sheet Material)
2c9bf601-2da9-57af-8eb2-2eb252527828 | button | External layer 1 - Product. | DHF,Ply H3 15,Ply H3 17,Ply H3 19,Other,Not applicable
549276be-7280-56d4-b086-933707b659b2 | button | External layer 1 - Fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
7afead34-9b42-58e6-ba4c-fd8d5f1548eb | button | External layer 1 - Fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
79181aab-0c90-50c6-87d3-ef272860e3d8 | button | Access or Removable sheets are labeled with ACCESS PANEL sticker | Yes,No,Not Applicable
544e5c5a-735f-5c49-b217-19b60de8a834 | note | External layer 1 - Take photos of panel, sheets and fixings.
5f658c08-3e11-59f0-81cf-0d269c2396fe | section | Step 7 - External Layer 2 (Membrane)
c21cc624-03f6-56e6-a1b0-d132337ede6b | checkpoint-no-value | Step 7 - External Layer 2 (Membrane)
d24f75c8-c108-55c1-b09d-115bd51d1849 | button | Product | Proclima Mento 3000 / Connect,Proclima Adhero,Other
6634d82c-3b4b-5b40-98cb-fd0e2d94cbdb | button | Fixings | None,Galvanised Staples
39425319-514d-5a11-96fe-982c62a57a5e | button | Membrane joints and laps as per specifications or shop drawings | Yes,No
5f11f31e-47f4-5a15-90d0-9aae19851d9e | button | Membrane overhangs as per shop drawings | Yes,No
6101bebc-49b0-540e-be47-7d02d3f98b42 | note | Take photos of panel with membrane and membrane joint (fold up if possible)
da934d50-18ef-5740-bb50-40336b6a91fa | section | Step 8 - External Layer 3 - Counter battens
dd8c2d71-4717-50ca-9585-58217868d0db | checkpoint-no-value | Step 8 - External Layer 3 - Counter battens
71969e5e-420c-5eca-9639-52aa9b1c7658 | button | Counter batten size | 45x20 (actual dimension),75x45 (actual dimension),Not Applicable
42dee86d-8efb-5d0c-a95f-71358fdacf09 | button | Product for tape under counter battens | Proclima Naideck,Not Applicable
4a31b6df-cdc4-5d7b-9224-a2977b39d8b2 | note | Take Photo of panel with counter battens. Add close up of tape under battens.
01c8fd12-8401-5a2b-9ac9-669d4763e3d7 | section | Step 9 - Final Sign Off
ce627f5b-1f50-54ca-a631-af6516d2eb4f | checkpoint | Step 9 - Final Sign Off
a71aec7c-beb4-5014-9828-df45af5f1784 | signoff | Sign off from Shift Leader.