## Master List Templates
Id | Type | Name | Values | Prompting Name
4f36f630-a755-4169-9a01-56ac270455b9/9 | checklist | A.ROF - Assembly Roof Installation |  | A.ROF - Roof Installation
9af3aba7-7c3a-4e74-954e-b4f8df273556 | section | Pre-Check
8e37ab3b-7f30-4cad-aba1-faf81269cf0d | checkpoint-no-value | Pre-Check
93d9699e-9f43-4729-b855-eae5f882270e | button | "For Construction" shop drawings available and current | Yes,No
877a799f-9314-4321-a85e-3b418e775173 | button | Structural Drawings available and current | Yes,No
8fa8c892-1fd5-42ca-bbc0-3b5d266c9aa1 | button | Wall panel installation below complete and safe to take roof panels | Yes,No
82e11dd9-266a-44aa-81fa-e87c1f0c6731 | button | Propping plan available (if applicable) | Yes,No,N/A
d3b96dd3-7203-4307-b69f-45d207843cef | button | Task Analysis (TA) in place | Yes,No
3c8b5176-695d-532b-aef3-6ea46eb1dcb7 | section | Structure
a9e07479-4649-5fbb-a7dc-a4a03e56ff1f | checkpoint-no-value | Installation
c2052e72-becd-5b0e-a416-d390650b576f | button | Panels landed tightly, interlocked with walls and other members as intended | Yes,No
9c6a1da8-5386-593f-b230-92fc492c4657 | button | Panels fixed to walls as per HENZ detail | Yes,No
15836dad-d445-5944-a16d-2a323ce49db2 | button | Panel joints fixed together as per HENZ detail | Yes,No
cb38432e-0471-53d6-9fbc-6060a36872ed | button | Intermediate supports fixed as per HENZ detail | Yes,No
91ec83d4-1aa3-506c-bfc5-b507fcd30b5f | button | Fixed to other panels/ members / exisiting members as per HENZ detail | Yes,No
9427f301-1c4f-5b4d-b723-c384f8bfd286 | button | Structural Engineer inspection before membrane is installed | Yes,No
5a8de0ca-604d-5827-b464-962f33df33c9 | note | Take photos of special structural fixings
4924564d-c531-5cb9-8676-2f92249f153d | section | Passive Fire, Acoustic
82f1f652-6b75-56a8-ba4f-04dffd4faaad | checkpoint-no-value | Passive Fire
861598ec-8491-5ab1-ac65-e631cb02c9e5 | button | Fire installations as per HENZ details | Yes,No,Not Applicable
0c60d187-d8fa-5354-a3e7-a9d0245f33d2 | button | Passive Fire is contineous (Red Pen Method) | Yes,No (raise with HENZ Project Manager),Not Applicable
4643a703-8821-569b-a29c-eecf6fdcca77 | note | Take photos of fire installations (concealed installations, seals on joints etc.)
a129d3bf-b0d7-5241-b0aa-2321ace87777 | checkpoint-no-value | Acoustic
cde5fff7-ec82-557c-b33b-8a96cbf246f6 | button | Sound insulation as per HENZ details | Yes,No,Not Applicable
0f5591f2-61f5-5cac-b41b-f2cbb76eae38 | note | Take photos of acoustic installations (concealed installations, seals etc.)
514050e9-f2c8-527c-bdf0-ffdc508d4cd4 | section | Thermal, Airtightness, Weather
2a83f225-da62-5b80-a6c8-49b2b862957c | checkpoint-no-value | Thermal
27358ec4-cc7c-518e-a5e4-8a3cc8f02985 | button | Insulation as per HENZ details | Yes,No,Not Applicable
243b1a44-cea2-5524-90c0-ae4d45363aef | button | Thermal is contineous (Red Pen Method) | Yes,No (raise with HENZ Project Manager),Not Applicable
7cf57804-d550-47a3-bbb2-ce26d7e1fecb | note | Take photos of thermal installations (concealed installations, at steel portals etc.)
5a11ffbf-96d7-5065-8219-0857d83bd832 | checkpoint-no-value | Airtightness
6fa0df25-00a7-54bd-a86f-5dc9eae2cc97 | button | Airtightness as per HENZ details - Kompri Band / Tapes / Other | Yes,No,Not Applicable
fb28e980-c899-5381-b8bf-911c7adf39be | button | Airtightness is contineous (Red Pen Method) | Yes,No (raise with HENZ Project Manager),Not Applicable
5645f4d1-6c18-4c5e-b901-3eb9300df06a | note | Take photos of acoustic installations (concealed installations, at steel portals etc.)
6ab24ff7-d759-5f42-b97a-787ed0db1fec | checkpoint-no-value | Weather and Watertightness
62669123-2118-5229-b11a-569c230c384f | button | Membrane Fitted, overlaps correct, joints taped, penetrations taped correctly | Yes,No,Not Applicable
f1752717-0bb4-505a-804f-e7623503ede4 | button | Counterbattens installed onto rafters below, Naideck tape under all battens | Yes,No,Not Applicable
60353e83-b0d1-574f-890d-e2f25af4c564 | button | Weather and watertightness as per HENZ details | Yes,No,Not Applicable
e50b8193-4d31-4c87-b016-c51c424e394b | note | Take photos of temporary covers if applicable
c528cf91-ffa7-57b7-841e-06f762ac5537 | section | Services
a45d594e-7c0a-5ab6-9da0-5344940f4d8d | checkpoint-no-value | Services
09359681-e274-5665-8e27-b8f54a303320 | button | Service interfaces linked / coupled / conduits etc. accessible and repaired | Yes,No,Not Applicable
bfe49e01-fcc2-538f-b094-85b366954942 | section | Final Check
bd8f18a2-e823-4f36-a8e6-9064a58cc3bd | checkpoint-no-value | Final Check Installer
1cefc334-936e-4a84-92c3-be5350b9597e | button | Clean away any debris | Yes,No
c7b5ae23-0376-4387-ae39-8f3f5d79adce | button | Ensure structure is covered to stop any water ingress | Yes,No
3fb40084-aab4-4ca8-b9c7-89ad76068568 | button | Area left safe, all fall hazards are eliminated | Yes,No
4991e077-acae-49eb-9d6b-7fa41dca8c2b | checkpoint | Final Installer Signoff
5d614f87-0556-509b-a82e-bab628e9ccbc | signoff:required | INSTALLER SIGN HERE OR REQUEST SIGNOFF
c49d350b-9900-4006-aa9c-c78ea10baace | checkpoint | Structural Engineer Inspection
6f020c9f-c889-54fb-a745-681067d3c01b | signoff:required | SIGN HERE OR REQUEST SIGNOFF
7354368f-bf96-5cd4-b5cb-32b288f55741 | section | Sign Off Sign Off
f80b7e38-ab44-4186-b882-62cdc4498d10 | checkpoint | Site Manager Signoff
519de42b-442f-4178-a6f6-ca701399f8b1 | signoff:required | SIGN HERE OR REQUEST SIGNOFF