## Master List Templates
Id | Type | Name | Values | Prompting Name
259914e1-cd4e-4a8f-b9f6-2a9ffd074a10/7 | checklist | Bi0e1Membrane - Balcony Panel - 0 Internal Layer - 1 External Layer - Membrane |  | R_000x
53d882cf-0fc8-4c65-bd1b-47a9fe5120be | section | Step 1 - Framing and Inside Layers
b7f02fdd-cc8a-4819-be95-c3eb72665b8a | checkpoint-no-value | Step 1 - Framing and Inside Layers
89c1c0a7-d212-4726-9bfc-9ac24f7105ba | button | Framing check for square. | Yes,No
49a24664-08ca-4f82-ac3a-3066062c3e8d | button | Structural fixings in frame are as per drawings. | Yes,No
a7516c2c-2e71-4a7c-89cc-2a1e7ef69ceb | button | Slings installed as per drawings. | Yes,No
b8dd02ea-ddd7-4ea7-9062-c11040415495 | note | Take Photos of frame, fixings and connections.
f76068e0-5325-53b5-b656-506ee8a16832 | section | Step 2 - External Layer 1 (Sheet Material)
d76412fc-8c46-4783-99ad-eb38e4095458 | checkpoint-no-value | Step 2 - External Layer 1 (Sheet Material)
9c86c33b-eca8-4bc6-9383-e9976440969e | button | External layer 1 - Product. | Ply H3 15,Ply H3 17,Ply H3 19,Ply H3 21,Other,Not applicable
8e398d51-c582-4086-8e34-67891eb5a4e5 | button | Deck framing supports at 400mm in one direction and Nogs/ Blocking at the sheet edges (all plywood edges supported) use 17mm minimum thickness (CCA H3.2 treated), structural plywood (Do not use tongue & groove plywood) | Yes,No
22e28d0c-7985-4b97-9e55-4f98b5038c5c | button | Plywood laid with face grain at right angles to supports. All sheet joins must be made on a single timber support to minimise the chance of movement between sheets. | Yes,No
892a4cd4-38f2-4a7e-8e0f-52aaa4a46e01 | button | Plywood is to be laid with staggered joins in a brick-bond pattern. Apply with a continuous bead of Holdfast Gorilla Grip 2 Hour-Cure Construction Adhesive on top of timber supports. | Yes,No
95750a7d-72a2-4686-85e7-b86c80734d62 | button | External layer 1 - Fixing treatment as per drawing. | Galvanised,Stainless,Other,None
da680fd7-2f67-44b9-86b8-0b70c30115fe | button | External layer 1 - Fixing type / size as per drawing. | Screws,Glue,Screw and Glue,None
49a80f90-84f4-4f32-8b57-e0ea1a5cb262 | button | Plywood screw-fixed with 10g x 50 or 65mm S/S counter-sunk screws at 150mm centres at all sheet edges and 200mm centres throughout the body of the sheet. All screws to be counter sunk 1-2mm. | Yes,No
1284f189-d3f6-4d98-8eac-ef6c6ed40eb4 | button | Glue sheet edges together. Continuous bead of 2 Hour-Cure Construction Adhesive (no spot gluing). Tight butt-joined, surface of the sheet joins. Glue must come to the top. Ensure joins and sheets are not walked on with two hours of application. | Yes,No
e430cf4c-e09e-4b73-bb1b-a2cf32fa2867 | button | Once sheets have been placed together remove excess adhesive by scraping the joint with a chisel. | Yes,No
c4629ccd-5476-49c4-aba7-893fded12f56 | button | When fully cured remove excess and sand all sheet joins | Yes,No
49efbba9-e4df-406b-8e09-b1deba8009c4 | button | Leave a 5mm expansion gap around the perimeter of the plane. | Yes,No
191bcdb5-745b-4ad3-a66f-1ee95103934f | button | Chamfer all external edges with a minimum radius of 5mm. | Yes,No
d06954d9-17c5-44d8-aefe-071a24767796 | button | Ensure compliant falls. E2/AS1 8.5.1. limitations state 2° for roofs (1:30 or 34mm/mt), 1.5° for decks (1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters | Yes,No
99849213-39e6-57db-9478-02bd072f2517 | section | Step 3 - External Layer 1 - Photos
7624d097-a0c6-47d4-9169-51faa4e523cc | checkpoint-no-value | Step 3 - External Layer 1 - Photos
7759da26-27ae-4f6f-81fd-6d7364d5cb37 | note | External layer 1 - Take photos of panel, sheets and fixings.
7fff95f4-49f9-56b8-ac3b-40a67fd1e5c1 | section | Step 4 - Final Sign Off
0e0c48fe-c468-410d-b2e3-ff910f62ebf5 | checkpoint | Step 4 - Final Sign Off
92c94eab-04e7-4d8f-8de3-796ec8bef0bb | signoff | Sign off from Shift Leader.