## Master List Templates
Id | Type | Name | Values | Prompting Name
31d7096f-79d5-407d-b065-ba47db0fb2f8/1 | checklist | IWi2e1 - 2 Internal Layer - 1 External Layer |  | IW_000x
3774480b-2202-5512-814c-5cd8ca745766 | section | Step 1 - Framing and Inside Layers
b6c81218-0325-5adc-9670-f13ec307b57d | checkpoint-no-value | Step 1 - Framing and Inside Layers
ffb006d6-53aa-5678-8e78-d9b8f4e70679 | button | Framing check for square. | Yes,No
e7955041-42de-5aa2-9a1b-f81d3a1d0c58 | button | Structural fixings in frame are as per drawings. | Yes,No
d0cce61f-4b18-505e-b63a-bf80d0376a79 | button | Slings installed as per drawings. | Yes,No
9e9a6f9f-acc6-586b-a3f9-bb138557c8fb | note | Take Photos of frame, fixings and connections.
bb4dfc91-411d-5a77-ab85-7cf366f6dc52 | section | Step 2 - Inside Layers
d20369a5-fe6b-59c6-8e37-0ec8b10b3e38 | checkpoint-no-value | Step 2 - Inside Layers
988861d1-6bcc-5405-b935-3946ff1b6cd4 | button | Internal layer 1 - product. | OSB15,OSB22,Ply UT 15,Ply H3 15,GIB10,GIB13,GIB16,OTHER,NOT APPLICABLE
06b3050e-8484-5c06-b9a0-dd3f526cb996 | button | Internal layer 1 - fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
c508edab-b88a-5a09-93af-9fb3a6cc91ce | button | Internal layer 1 - fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
92fadfef-253a-5280-a349-279ee57c95fd | button | Internal layer 2 - product. | OSB15,OSB22,Ply UT 15,Ply H3 15,GIB10,GIB13,GIB16,OTHER,NOT APPLICABLE
67352a51-7691-5700-93a8-c8fb4fa475ef | button | Internal layer 2 - fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
d550f882-bbb6-5479-9aec-59eed1f2d1cf | button | Internal layer 2 - fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
4dcb7204-47f0-5111-90c5-52940cce07fa | section | Step 3 - Services
60938db8-8ea5-5ef6-9fa6-56f3452311be | checkpoint-no-value | Step 3 - Services
074abd9b-22fd-5d4f-8423-16bf6afc6d40 | button | Services - Fire rated wall, use fire rated flush box. Do not alter flush boxes. | Yes,No
97f8c797-2453-55fe-a422-681e2a6b0e62 | button | Services - Conduits terminated and run to best practice and as per drawings. | Yes,No
26f9623d-1597-59f5-9c9b-3338caa6f0d2 | button | Services - Airtightness - penetrations are sealed. | Yes,No
14442b67-4763-5f20-8940-f55d3460c50b | button | Services - Fire rated wall, all penetrations treated as per drawings (i.e. gib lined or so) | Yes,No
af59bf63-2f4f-5429-b673-a5423a6300b1 | note | Take photos of flush boxes, fire treated penetrations, conduit terminations.
987d8171-da86-5327-8ecd-f635ef8df782 | section | Step 4 - Insulation
3d3cfaa4-8f12-545b-9a1c-58a29b5771cf | checkpoint-no-value | Step 4 - Insulation
d5c2413b-10b2-5744-ae79-070072395609 | button | Insulation as per drawing. Tight fit, no gaps, no squeeze. | R2.6,R2.8,R4.1,None
012ce5b2-4fb0-52b6-8176-92a35cfff875 | note | Take photos of finished insulation.
5fd14ab0-6fc4-52c1-9326-7079ea2fb858 | section | Step 5 - External Layer
cdfaf3cc-8c11-587d-8f16-82890e0b0c04 | checkpoint-no-value | Step 5 - External Layer
b2c64429-bb57-5122-bc58-d211c99859c1 | button | External layer 1 - product. | MEMBRANE,OSB15,OSB22,Ply UT 15,Ply H3 15,GIB10,GIB13,GIB16,OTHER,NOT APPLICABLE
b0835722-465f-5802-bdaf-b757eb0d2656 | button | External layer 1 - fixing treatment as per drawing. | Blank,Galvanised,Stainless,Ceramic Coated,Other,None
7164d659-8105-57e4-bfe5-75093fb8da22 | button | External layer 1 - fixing type / size as per drawing. | Staples45,Staples65,Nails,Screws,Glue,Screw and Glue,None
9ca471f3-6486-5d0d-a541-2bf0b133f5bb | button | Panel completed, no defects, no damage. | Yes,No
0aaf38a9-b849-5cdb-a258-b7543ea3cddf | note | External layer 1 - take photos of fixings and final panel.
846e7710-ff62-53a7-b507-d80d1f644c39 | section | Step 6 - Final Sign Off
a6f1da6d-7d83-5296-b3d9-99eaf85e8cc1 | checkpoint | Step 6 - Final Sign Off
73db703f-c125-50fb-99e4-4138c69796ce | signoff | Sign off from Shift Leader.